## Sheet1
Resource Loading Milestone
# | Feature |  |  | Estimated Hours |  | Remaining Hours |  | Completion | Comment
1 | Message & Event System |  |  | 8 |  | 8 |  | 0% | [[COGLISTENER]] functions, detect virtuals and generate static calls for subs
2 | File Loading System |  |  | 2 |  | 2 |  | 0% | Load in X separate threads, use message system to signal file read
3 | Resource System |  |  | 4 |  | 4 |  | 0% | Resource loading, bulk loading (?), only one instance per resource,
4 | Resource Caching System |  |  | 4 |  | 4 |  | 0%
5 | Move Cog stuff from Game to Cog project |  |  | 2 |  | 2 |  | 0%
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
SUM |  |  |  | 20 |  | 20 |  | 0%
Current Date | 2019-11-29 23:34 |  | Expired Days | 0 |  | Expired hours | 0 | hours | Hours per week | 11
Milestone Start | 2019-11-29 |  | Expired Workdays | 0 |  | Expired workday hours | 0 | hours | Hours per workday | 1
Milestone End | 2019-12-12 |  | Expired Weekend Days | 0 |  | Expired weekend hours | 0 | hours | Hours per weekday | 3
Total days | 14
Workdays | 10
Weekend days | 4 |  | Worked hours | 0 | hours
Total hours (capacity) | 22 |  | Expected remaining hours | 20 | hours
|  |  | Actual remaining hours | 20 | hours
Scope | 20 | hours | Hours behind | 0 | hours
Capacity | 22 | hours
Scope vs Capacity | 90.91%
Formulas:
Estimated Hours = DAYS([Feature],[Feature, row below])
Estimated Hours = MIN(C31, MAX(0, NETWORKDAYS([Feature],[Feature, row above])-1))

## Sheet2
It works