## Sheet1
Prebuild Milestone
# | Feature |  |  | Estimated Hours |  | Remaining Hours |  | Completion | Comment
1 | Make milestone spreadsheet |  |  | 4 |  | 0 |  | 100%
2 | HeaderTool generate projects flag |  |  | 4 |  | 0 |  | 100% | Generate VS files for every project in config
3 | Generate typelist from header tool |  |  | 3 |  | 0 |  | 100% | Includes specializations
4 | Generated header file and GENERATED_BODY |  |  | 4 |  | 0 |  | 100% | Should check for .generated.h includes for files with COGTYPEs
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
SUM |  |  |  | 15 |  | 0 |  | 100%
Current Date | 2019-11-15 22:49 |  | Expired Days | 11 |  | Expired hours | 15 | hours | Hours per week | 11
Milestone Start | 2019-11-04 |  | Expired Workdays | 9 |  | Expired workday hours | 9 | hours | Hours per workday | 1
Milestone End | 2019-11-17 |  | Expired Weekend Days | 2 |  | Expired weekend hours | 6 | hours | Hours per weekday | 3
Total days | 14
Workdays | 10
Weekend days | 4 |  | Worked hours | 15 | hours
Total hours (capacity) | 22 |  | Expected remaining hours | 0 | hours
|  |  | Actual remaining hours | 0 | hours
Scope | 15 | hours | Hours behind | 0 | hours
Capacity | 22 | hours
Scope vs Capacity | 68.18%
Formulas:
Estimated Hours = DAYS([Feature],[Feature, row below])
Estimated Hours = MIN(C31, MAX(0, NETWORKDAYS([Feature],[Feature, row above])-1))

## Sheet2
It works